## Sheet1
Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story?
1 | As an admin I should be able to create Announcements and updates on Subdomain homepage “Nebny" | 5 | aya | creation of home page | marwan
1.1 | As an admin I should be able to update Announcements and updates on Subdomain homepage “Nebny | 5 | aya | creation of announcements | marwan
1.2 | As an admin I should be able to delete Announcements and updates on Subdomain homepage “Nebny | 2 | aya | creation of announcements | marwan
1.3 | As a user I should be able to read Announcements and updates on the AWG hub | 2 | aya | creation of announcements | marwan
1.4 | As a user I should be able to read Announcements and updates on Subdomain homepage “Nebny | 2 | marwan | creation of announcements | aya
1.5 | As a user I should be able to create a question in FAQ section | 5 | marwan | creation of FAQ section | aya
1.6 | As a user I should be able to delete a question in FAQ section | 2 | marwan | creation of FAQ section | aya
1.7 | As a user I should be able to update a question in FAQ section | 3 | marwan | creation of FAQ section | aya
1.8 | As an Admin I should be able to create an answer in FAQ section | 5 | aly | creation of FAQ section | ahmed
1.9 | As an Admin I should be able to update an answer in FAQ section | 3 | aly | creation of FAQ section | ahmed
2 | As an Admin I should be able to delete an answer in FAQ section | 2 | aly | creation of FAQ section | ahmed
2.1 | As a user I should be able to read questions and answers in the FAQ section | 2 | aly | creation of FAQ section | ahmed
2.2 | As an admin I should be able to read questions and answers in the FAQ section | 2 | aly | creation of FAQ section | ahmed
2.3 | As an Admin ‘EE member’ I should be able to create products with its prices to the page “our products” | 8 | karim | creation of our products page | naiem
2.4 | As an Admin ‘EE member’ I should be able to update products with its prices to the page “our products” | 8 | karim | creation of our products page | naiem
2.5 | As an Admin ‘EE member’ I should be able to delete products with its prices to the page “our products” | 5 | karim | creation of our products page | naiem
2.6 | As a user I should be able to read products with its prices in the page “our products" | 2 | karim | creation of our products page | naiem
2.7 | As a user I should be able to create a cart in the subdomain "Nebny" | 8 | sarah | creation of products | nagham
2.8 | As a user I should be able to update a cart in the subdomain "Nebny" | 5 | sarah | creation of products | nagham
2.9 | As a user I should be able to delete a cart in the subdomain "Nebny" | 3 | sarah | creation of products | nagham
3 | As a user I should be able to read a message ackownledging me with the code of my order | 2 | sarah | creation of products | nagham
3.1 | As an "Skills In Mansheya" Admin I should be able to create Profiles of workshop owners at “Skills In Mansheya” page | 8 | naiem | creation of "Skills in Mansheya" page | karim
3.2 | As a User I should be able to read Profiles of workshop owners at “Skills In Mansheya” page | 2 | naiem | creation of profiles | karim
3.3 | As a User I should be able to create a request for a certain skill or craft in “skills in Mansheya” | 5 | naiem | creation of profiles | karim
3.4 | As a User I should be able to delete a request for a certain skill or craft in “skills in Mansheya” | 2 | naiem | creation of profiles | karim
3.5 | As an“Skills In Mansheya”Admin I should be able to read a notification when a User requests a certain skill or craft | 8 | naiem | creation of a request | karim
3.6 | As a User I should be able to create a suggestion in the suggestion box in the "educational programs" page | 3 | nagham | creation of a suggestion box | sarah
3.7 | As a User I should be able to read a message "Thank you" after writing a suggestion | 2 | nagham | creation of a suggestion | sarah
3.8 | As an Admin I should be able to read suggestions written in the suggestion box | 2 | nagham | creation of a suggestion | sarah
3.9 | As a "Portofolio"Admin I should be able to create 6 groups with children names | 8 | seif | creation of "portifolio page" | tarek
4 | As a "Portofolio"Admin I should be able to create children info | 8 | seif | creation of "portifolio page" | tarek
4.1 | As an Admin I should be able to read the children's info | 5 | seif | creation of children's name | tarek
4.2 | As a "Portofolio"Admin I should be able to update children info | 8 | seif | creation of children's name | tarek
4.3 | As a "Portofolio"Admin I should be able to delete children info | 3 | seif | creation of children's name | tarek
4.4 | As an Admin I should be able to "add" update photos to Gallery | 5 | ahmed | creation of "Gallery" page | aly
4.5 | As an Admin I should be able to Delete photos from Gallery | 2 | ahmed | Uploading of photos to Gallery | aly
4.6 | As a User I should be able to read Gallery | 2 | ahmed | Uploading of photos to Gallery | aly
4.7 | As an Admin I should be able to create online recruitment form at the recruitment page | 3 | tarek | creation of recruitment page | askary
4.8 | As an Admin I should be able to delete online recruitment form at the recruitment page | 2 | tarek | creation of recruitment form | askary
4.9 | As an Admin I should be able to update online recruitment form at the recruitment page | 3 | tarek | creation of recruitment form | askary
5 | As a User I should be able to read an online recruitment form | 2 | tarek | creation of recruitment form | askary
5.1 | As a User I should be able to create an online recruitment application | 3 | tarek | creation of recruitment form | askary
5.2 | As an Admin I should be able to create a confirmation message if the applicant chose a slot | 5 | askary | Applicant choosing a slot | seif
5.3 | As an Admin I should be able to create a confirmation message if the applicant came at slot timing | 5 | askary | applicant comping at slot timing | seif
5.4 | As an Admin I should be able to create a confirmation message if the applicant rescheduled | 5 | askary | Applicant rescheduled | seif
5.5 | As an Admin I should be able to create a confirmation message if the applicant didnt came at slot timing | 5 | askary | Applicant didn’t come at slot timing | seif